S-ATET Program Plan

- Dates

5th – 8th February, 2018

- Venue

Royal Palm resort Pvt. Ltd.

Kundhar, Pokhara

Nepal

- Goal

- To empower students to be an entrepreneur based on appropriate technology

- PU MITE faculty capacity development by their lecturing and facilitation of the S-ATET program

- Target

- PU students (undergraduate & postgraduate)

- Students from PU affiliated colleges

- Outcome

- Students can acquire the necessary elements for starting a business such as business and technical skills, and entrepreneurship.

- PU MITE faculty members can learn basic knowledge and teaching methods for the MITE course.

- Implementable business ideas: Minimum 2 cases

- Methodology/ Procedures

In order to achieve the goal setup through the target group interactive participative method of delivery will be followed. The various activities as listed below will be performed.

Activity-I: Workshop organizing committee and Evaluation committee will be established. Target groups are informed via Notice board and letter to the concerns schools/colleges.

Activity-II: Proposals (Area: Energy, Environment, Agriculture, tourism, …) will be called from students (group consists of participants from different departments). Best among the submitted projects will be selected and number of projects will be decided based on the capacity of participants. This will be done from expert panel review.

Activity-III: Motivational activity: established social entrepreneurs will be called for;

- Innovative social entrepreneurs’ interaction

- Simulation and role play

- Case based analysis/ situation

- Students in parallel work to shape up their concepts in the allocated time.

Activity-IV: Presentation/Discussion of selected projects by students in group. Group of         professors closely observe the projects and guide them. Based on the guidelines and suggestions student had to further review their concept and modify till the level to business establishment.

- Participants

Forty students (undergraduate & postgraduate) will participate in the workshop from PU and PU affiliated colleges (Pokhara area). Proposals from the group of students (intra/inter school) will be called, members from the selected proposals will participate in the workshop. In case, if the proposals are not sufficient to meet the targeted population of participants then the remaining number will be fulfilled from each school based on the quality/interest of individual students. The coordinators of the school will role in the recommendation of students.

- Curriculum

Course duration: 4 days

Group of students present their business ideas and based on that lecturers and tutors evaluate and guide them throughout the workshop followed by the presentation, comments and suggestions to knowledge sharing to shape the ideas to best business models. At the end students give the final presentation with vigorous remodeling through the support of lecturers’ ideas and guidance. Topics of presentations are:

- Social entrepreneurship with examples of best cases

- Introduction to problem definition and Business planning

- Detail concept on business model design

- Basic concept on Feasibility analysis

- Introduction to Appropriate technology in Nepal

- Product development, market research and Simulation & Role play

- Legal and ethical Issues

- Interaction with Innovative social entrepreneur

- Pitching sessions in the evening and after dinner: During these sessions students completely work on their projects/Business Model/presentation in group. Tutors and mentors will closely guide/instruct them. Role plays are conducted for experience sharing of established social entrepreneur.

- Program Schedule

| DATE | 05 Feb | 06 Feb | 07 Feb | 08 Feb |
| --- | --- | --- | --- | --- |
| DAY | 1st day (Mon) | 2nd day (Tue) | 3rd day (Wed) | 4th day (Thurs ) |
| 9:00 - 10:00 (60’) | Registration & Opening Ceremony | Review & Discussion/ Interaction with social entrepreneur (45’) | Review & Discussion/ Simulation and role Play (60’) | Market Research Discussion Activity (Umesh Yadav) (60’) |
|  |  | Business Model I (Surya GC) (40’) Lecture | Introduction to Product Development (Yunseon Kim) Lecture (60’) |  |
| 10:00 - 11:00 (60) | Social Entrepreneurship (Ajay Thapa) (60’) Lecture |  | Business Plan (Rabindra Ghimire) (50’) Lecture | Business Plan (Mentor ) Activity (120’) |
|  |  | Business Model II (Surya GC) (40’) Activity |  |  |
| 11:00 - 12:00 (60’) | Problem Definition ( Prof. Tek raj Gayawali ) (90’) Lecture | Business Model III (50’) (Rabindra Ghimire) Activity | students problems Identification (30’) |  |
| 12:00 - 13:00 (60’) | Lunch Break (60’) | Lunch Break (60’ | Lunch Break (60’ | Lunch(60’) |
| 13:00 - 14:30 (90’) | Proposal Presentation by Students/ Comments by tutors | Feasibility Analysis (Surya GC) 50’ Lecture | Legal & ethical issues (Yograj Lamichhane) (90’) | Final Presentation By Students 120’ |
|  |  | AT in Nepal (Sanjeev Thapa) (40’) Lecture | Market Research (200’) Activity/ Parallelly Students should work on their Proposals |  |
| 14:30 - 16:00 (90’) | Proposal Presentation by Students/ Comments by tutors | Mentor allocation to each group/ direct Guidance /supervision/ remodeling the concept (150’) |  |  |
|  |  |  |  | Closing Ceremony (30’)/Awarding seed money to best 2 groups |
| 16:00 - 17:00 (60’) | Market Research Method/Visit to site (Umesh Yadav) (90’) Lecture |  |  |  |
| 17:00 – 17:30 | Tea Break |  |  |  |
| 17:30- 18: 30 | Pitch-I : Discussion session among students/Role Play |  |  |  |
| 18:30 – 19:30 | Pitch-II: guidance/Working on business Model/Role Play |  |  |  |
| 19: 30 -20:30 | Dinner time |  |  |  |
| 20:30 – 10:00 | Pitch-III: finding Appropriate Technology/Developing Business Model/ preparation for next day presentation |  |  |  |